## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | OMKAR NANDKUMAR MORE
Document Created On: | 2026-06-08
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## PROJECT SCHEDULE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Absence of Insights – Student Economic Background, Academic Performance & Expected Salary |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | GPI Data Analytics Project – EDA & Visualization Outputs
PROJECT SCOPE | Exploratory Data Analysis on student dataset answering 17 GPI analytical questions
PROJECT START DATE | 2026-05-07
PROJECT END DATE | 2026-07-02
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation
1.1 | Identify business problem | Omkar Nandkumar More | 2026-05-07 | 2026-05-08 | 2 | COMPLETED
1.2 | Review GPI problem statement | Omkar Nandkumar More | 2026-05-07 | 2026-05-08 | 2 | COMPLETED
1.3 | Create project charter | Omkar Nandkumar More | 2026-05-09 | 2026-05-10 | 2 | COMPLETED
1.4 | Dataset familiarization | Omkar Nandkumar More | 2026-05-09 | 2026-05-10 | 2 | COMPLETED
2 | Planning
2.1 | Work Breakdown Structure (WBS) | Omkar Nandkumar More | 2026-05-11 | 2026-05-12 | 2 | COMPLETED
2.2 | Project Schedule | Omkar Nandkumar More | 2026-05-11 | 2026-05-12 | 2 | COMPLETED
2.3 | RAID Log | Omkar Nandkumar More | 2026-05-13 | 2026-05-13 | 1 | COMPLETED
2.4 | Requirement Elicitation Questionnaire | Omkar Nandkumar More | 2026-05-13 | 2026-05-14 | 2 | COMPLETED
2.5 | Software Requirement Specifications (SRS) | Omkar Nandkumar More | 2026-05-14 | 2026-05-15 | 2 | COMPLETED
3 | Execution
3.1 | Data Loading & Cleaning | Omkar Nandkumar More | 2026-05-16 | 2026-05-17 | 2 | COMPLETED
Features
Import libraries & load dataset
Strip whitespace from column names
Map Family Income to numeric midpoints
Handle null values
3.2 | Basic Questions Analysis (Q1–Q9) | Omkar Nandkumar More | 2026-05-18 | 2026-05-25 | 8 | COMPLETED
Tasks
| Q1 – Unique student count |  | 2026-05-18 | 2026-05-18 | 1 | COMPLETED
| Q2 – Average GPA |  | 2026-05-18 | 2026-05-18 | 1 | COMPLETED
| Q3 – Student distribution by graduation year |  | 2026-05-18 | 2026-05-18 | 1 | COMPLETED
| Q4 – Python experience distribution |  | 2026-05-18 | 2026-05-18 | 1 | COMPLETED
| Q5 – Average family income |  | 2026-05-18 | 2026-05-18 | 1 | COMPLETED
| Q6 – GPA by college (Top 5) |  | 2026-05-22 | 2026-05-22 | 1 | COMPLETED
| Q7 – Outlier detection in Quantity (IQR + boxplot) |  | 2026-05-22 | 2026-05-22 | 1 | COMPLETED
| Q8 – Average GPA per city (Top 10) |  | 2026-05-22 | 2026-05-22 | 1 | COMPLETED
| Q9 – Family income vs GPA correlation |  | 2026-05-22 | 2026-05-22 | 1 | COMPLETED
3.3 | Moderate Questions Analysis (Q10–Q17) | Omkar Nandkumar More | 2026-05-23 | 2026-05-23 | 11 | COMPLETED
Tasks
| Q10 – City-wise student count (Tableau Public) |  | 2026-05-23 | 2026-05-23 | 1 | COMPLETED
| Q11 – Expected salary vs GPA, Income, Python exp |  | 2026-05-23 | 2026-05-23 | 1 | COMPLETED
| Q12 – Events attracting most unique colleges |  | 2026-05-23 | 2026-05-23 | 1 | COMPLETED
| Q13 – Leadership vs GPA & expected salary |  | 2026-05-26 | 2026-05-26 | 1 | COMPLETED
| Q14 – Students graduating by end of 2024 |  | 2026-05-26 | 2026-05-26 | 1 | COMPLETED
| Q15 – Promotion channel analysis |  | 2026-05-26 | 2026-05-26 | 1 | COMPLETED
| Q16 – Data Science event attendance count |  | 2026-05-26 | 2026-05-27 | 2 | COMPLETED
| Q17 – High CGPA + Python exp vs average salary |  | 2026-05-27 | 2026-05-30 | 3 | COMPLETED
3.4 | Tableau Public Dashboard | Omkar Nandkumar More | 2026-05-23 | 2026-05-24 | 2 | COMPLETED
Features
Aggregate city-wise data using Python
Upload summarized CSV to Tableau Public
Build interactive bar chart dashboard
Publish and capture dashboard URL
3.5 | Testing & Validation | Omkar Nandkumar More | 2026-06-03 | 2026-06-05 | 3 | COMPLETED
Features
Re-run full notebook end to end
Verify all chart outputs are correct
Cross-check conclusions against outputs
4 | Documentation
4.1 | Project Submission Document | Omkar Nandkumar More | 2026-06-03 | 2026-06-06 | 4 | COMPLETED
Features
Compile all code blocks
Insert all chart outputs
Write conclusions for all 17 questions
4.2 | Project Report | Omkar Nandkumar More | 2026-06-05 | 2026-06-05 | 3 | COMPLETED
Features
Write background and introduction
Write methodology section
Fill targeted vs achieved table
Write conclusion and future scope
4.3 | Lessons Learnt Log | Omkar Nandkumar More | 2026-06-07 | 2026-06-07 | 1 | COMPLETED
5 | Closure
5.1 | Final review of all deliverables | Omkar Nandkumar More | 2026-06-08 | 2026-06-08 | 1 | COMPLETED
5.2 | Upload all files to GPI portal | Omkar Nandkumar More | 2026-06-08 | 2026-06-08 | 1 | COMPLETED