## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Absence of Insights for the Relationship Between Student's Economic Background, Academic Performance, Competence & Expected Salary
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-05-07
EXPECTED COMPLETION DATE | 2026-07-02
ESTIMATED COST | N.A. (GPI Internship – No Direct Cost)
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To analyze the relationship between students' economic background (family income), academic performance (CGPA), technical competence (Python programming experience), and expected salary using Exploratory Data Analysis (EDA) in Python and interactive visualization in Tableau Public, thereby generating actionable insights for academic institutions and career counseling teams
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Academic institutions and career counseling organizations currently lack data-driven insights into how a student's economic background and academic performance influence their career expectations. Cloud Counselage's GPI dataset contains rich student records that remain underutilized. By systematically analyzing this data, the project will help recruiters and counselors make evidence-based decisions, improving placement outcomes and personalized career guidance for students.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Answer a minimum of 8 Basic analytical questions with Python code, visualizations, and written conclusions Answer a minimum of 8 Moderate analytical questions with Python code, visualizations, and written conclusions Build one interactive Tableau Public dashboard for city-wise student distribution (Q10) Complete all 8 GPI deliverable documents within the 120-hour project timeline Compute Pearson correlation coefficients for at least 3 variable pairs (income–GPA, Python exp–salary, GPA–salary)
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Project Submission Document (Python codes, chart outputs, and conclusions), Project Report (background, methodology, targeted vs. achieved, and conclusion), Project Charter, Work Breakdown Structure (WBS) in PPTX format, Project Schedule in XLSX format, RAID Log in XLSX format, Requirement Elicitation Questionnaire in XLSX format, Software Requirement Specifications (SRS) in XLSX format, Lessons Learnt Log in XLSX format, and Tableau Public Dashboard for city-wise student distribution.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Exploratory Data Analysis (EDA) on the provided student dataset, answering all 17 GPI analytical questions (9 Basic and 8 Moderate), statistical and correlation analysis covering CGPA, family income, Python experience, and expected salary, data visualization using Python (Matplotlib and Seaborn) and Tableau Public, and completion and submission of all 8 GPI project management documents.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Collecting new or additional student data beyond the provided dataset, building machine learning or predictive salary models, real-time data pipelines or database integration, mobile or web application development, and any analysis beyond the 17 questions defined in the problem statement.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Intern from the Data Analytics Domain, responsible for all analysis, visualization, and documentation.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Google Colab as a cloud-based Python runtime environment, Tableau Public as an interactive data visualization tool, Microsoft Excel as the dataset source format (.xlsx), Python libraries including pandas, matplotlib, seaborn, and openpyxl, Cloud Counselage Mentor and Domain Lead Harshada Topale for guidance and review, and GPI Workshop Recordings covering Project Planning and Data Analytics modules.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | All tools and platforms used in this project are free and open-source, including Google Colab, Tableau Public, and Python libraries (pandas, matplotlib, seaborn, and openpyxl). No hourly, monthly, or yearly cost is allocated, as this is a GPI internship project with no direct budget requirement.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Tushar Topale, Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Tushar Topale as Project Sponsor, Harshada Topale as Project Manager and Domain Lead, Omkar Nandkumar More as the Data Analytics Intern and project executor, academic institutions as end beneficiaries of the insights generated, and recruiters and career counselors as secondary beneficiaries.
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | The dataset may contain missing or null values in critical columns such as CGPA, family income, and expected salary, which could lead to incorrect analysis results. Google Colab session timeouts may cause loss of in-memory variables mid-analysis. Tableau Public's free tier file size limitation may prevent full dataset upload for the city-wise visualization question. Ambiguous interpretation of moderate questions may require rework and additional time. Single-resource dependency on one intern means any unavailability directly delays project delivery.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | The student dataset provided by Cloud Counselage is assumed to be accurate and complete. Email IDs are assumed to uniquely identify each student with no duplicates. Family income bracket midpoints are assumed to be reasonable numeric proxies for correlation analysis, mapping 0–2 Lakh to 1, 2–5 Lakh to 3.5, 5–7 Lakh to 6, and 7 Lakh and above to 8. The Leadership Skills column is assumed to contain only yes or no values after data cleaning. Internet access and Google Colab availability are assumed to be maintained throughout the project duration.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | The project must be completed within the 240-hour GPI internship timeline from 07 May to 02 July 2026. Only free and open-source tools may be used, with no paid software licenses permitted. The provided dataset cannot be redistributed outside Cloud Counselage. The project is an individual assignment, and no team collaboration is permitted. All deliverables must strictly follow the Cloud Counselage GPI templates provided.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2026-05-14
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2026-05-21
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-05-25
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-05-28
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 2026-06-03
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 2026-06-05
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-06-08