## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 4 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Absence of Insights – Student Economic Background, Academic Performance & Expected Salary | Absence of Insights – Student Economic Background, Academic Performance & Expected Salary | Project Id: | GPI-DA-IP-11449 | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1.O |  | Last Updated date: | 2026-06-06 | Project Team Lead: | Omkar Nandkumar More |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 11 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Dataset may contain missing or null values in key columns (CGPA, Family Income, Expected Salary). | Incorrect analysis results and misleading visualizations. | Perform null-value checks at start; use median imputation or exclusion for missing records. | Omkar Nandkumar More | High | 12 | Closed | Risk
2 | Risk | Google Colab session timeout causing loss of in-memory data. | Re-processing required; potential delay in delivery. | Save cleaned DataFrame to CSV after preprocessing; re-load at session start. | Omkar Nandkumar More | Moderate | 6 | Closed | Assumption
3 | Risk | Tableau Public file size limit exceeded for city-wise visualization. | Q10 (Moderate) visualization could not be completed as required. | Pre-aggregate data using Pandas before uploading; reduce dataset to summary statistics. | Omkar Nandkumar More | Moderate | 6 | Closed | Issue
4 | Assumption | Email IDs in the dataset are unique per student. | If email IDs are duplicated, unique student count will be overestimated. | Verified via df['Email ID'].duplicated().sum() — confirmed no duplicates. | Omkar Nandkumar More | Low | 0 | Closed | Dependency
5 | Assumption | Income bracket midpoints (0-2L→1, 2-5L→3.5, 5-7L→6, 7L+→8) are reasonable approximations. | Correlation with GPA/Salary may be slightly biased. | Acknowledged as a limitation; disclosed in project report methodology section. | Omkar Nandkumar More | Low | 0 | Closed
6 | Issue | Family Income stored as string categories, not numeric — direct correlation not possible. | Could not compute Pearson correlation between income and salary/GPA directly. | Mapped income categories to numeric midpoints using a Python dictionary (income_map). | Omkar Nandkumar More | High | 0 | Closed | Open
7 | Dependency | Tableau Public tool availability and internet access required for Q10 visualization. | If Tableau Public is down or inaccessible, Q10 visualization cannot be submitted. | Alternative: Use Matplotlib/Seaborn horizontal bar chart as fallback (implemented). | Omkar Nandkumar More | Moderate | 0 | Closed | Closed
8 | Risk | Loss of unsaved work and delay in project completion. | Loss of unsaved work and delay in project completion. | Regularly save notebook to Google Drive; download local copy after every major section. | Omkar Nandkumar More | Low | 3 | Closed
9 | Assumption | The 'Events' column correctly reflects the actual event each student attended as recorded by Cloud Counselage. | If event names are inconsistent or misspelled, event-wise analysis (Q12, Q16) may produce incorrect groupings. | Applied str.lower() and keyword matching to standardize event names before analysis. | Omkar Nandkumar More | Low | 0 | Closed | Critical
10 | Issue | Column name 'Leadership- skills' contained inconsistent spacing and casing across rows. | Groupby operations on leadership column returned incorrect or incomplete results. | Applied str.strip() and str.lower() to standardize all values to 'yes' or 'no' before analysis. | Omkar Nandkumar More | Moderate | 0 | Closed | High
11 | Dependency | The project is dependent on the dataset file provided by Cloud Counselage remaining unchanged throughout the analysis period. | Any changes or updates to the dataset mid-project would require re-running all analyses from scratch. | Downloaded and saved a local copy of the dataset at the start of the project; used only that fixed version. | Omkar Nandkumar More | Low | 0 | Closed | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24